## Final
Experience Nepal - Timeline ¦ By KC ¦
Final Version
Milestone | Task | Budgeted Hours | Due Date
Initial Project Proposal | Establish project goal | 0.1 | 2019-04-09
| Research and define target audience | 1.5
| Create Personas | 0.5
| List objectives | 0.1
| Detail overall content and page content | 0.5
| Create a deliverables | 0.5
| Write about content treatment | 0.3
| Discuss the delivery platform | 0.1
| Cover the media assets the project will use | 0.5
| Write about possible ethical / legal issues | 0.2
| Breakdown into tasks and create time estimates | 0.4
| Proof of read and edit text | 1
| Generate copyright license | 0.1
| Polish document design | 0.7
| Final proof of read | 0.5
Subtotals |  | 7
Initial Navigation Map | Planning | 0.1 | 2019-04-16
| Creating pages | 0.4
| creating path | 0.3
| Final navigation map | 0.2
Subtotals |  | 1
Initial Risk Assessment | Brainstorm risks | 0.6 | 2019-04-23
| Create text for risks | 0.4
| Research probabilities | 0.5
| Final proof of read & spell check | 0.5
Subtotals |  | 2
Initial Test Plan | Write up the objectives of the test plan | 0.5 | 2019-04-30
| Decide and write about a testing approach and assumptions | 0.3
| Decide and write down what features and functionality will be tested | 0.3
| Detail what my expected results will be | 0.4
| Decide and write what the deliverables will be | 0.5
| Write up the test documentation | 1
| Write down what the testing procedures and walkthroughs are | 0.5
| List the schedules of when testing will take place | 0.5
Subtotals |  | 4
Initial Storyboard | Write rough draft of what each webpage contains | 1 | 2019-04-30
| Draw a draft of how the website and webpages will look | 2
| Analyse the designs and consider changes | 0.5
| Modify the drafts | 2
| Collect feedback on storyboard | 0.5
| Make final changes and storyboard design | 3
Subtotals |  | 9
Media & Design Created | Write text for pages | 2
| Take and collect photos to use | 1
| Collect a range of fonts to possibly use for the logo and website in general | 1
| Create the logo | 0.5
| Reduce photo file size | 1
| Create the two unique graphics to use | 2
| Create the two unique animations to use | 3
| Create the two videos to use | 3
| Find suitable music for one video and edit it | 2.3
| Record a voice over | 0
| Compare formats for media and decide which to use | 1
| Test playback on various devices of media | 1
| Decide on colour scheme for the website | 2
| Create home page | 4
| Create media page | 2
| Create accommodation page | 2
| Create overview page | 1
| Create transport page | 1.5
| Create things to do page | 1
| Create contact page | 1.5
| create destination page | 1
| Create about us page | 0.2
Subtotals |  | 34
Submit Prototype | Add more detail to storyboard | 1 | 2019-05-31
| Create basic page layout in HTML | 3
| Create basic navigation bar and footer | 1.5
| Put temporary photos and content in | 1
| Collect feedback | 0.5
| Plan changes | 1
| Apply changes | 0.5
| Test project | 0.5
| Present draft prototype for feedback | 2
| Analyse feedback, plan and implement changes | 1
Subtotals |  | 12
Final Project | Final documentation | 9 | 2019-06-14
| Check of project requirements and testing | 5
| Final debug & test | 4
Subtotals |  | 18
TOTALS: (Hours) |  | 87

## Initial
Project Title: | Experience Nepal
Submitted by: | KC Bishwash
Submitted to: | Dr David Weir
Milestone | Item | Budgeted Hours | Actual Hours | Total Hours (to date) | Due Date | Budgeted Start Date | Budgeted Completed Date | Actual Start Date | Actual Completed Date | Variance (Hours)
Proposal Form / Creative Brief | Plan | 2 | 2 | 2 | 2019-06-07 | 2019-04-03 | 2019-04-12 | 2019-04-03 | 2019-04-05 | 0
| Writing document | 3 | 4 | 6 | 2019-06-07 | 2019-04-04 | 2019-04-12 | 2019-04-05 | 2019-04-05 | 1
| Edit | 1 | 1 | 7 | 2019-06-07 | 2019-04-05 | 2019-04-12 | 2019-04-05 | 2019-04-05 | 0
Subtotal: |  | 6 | 7
Navigation Map | Plan | 1 | 1 | 8 | 2019-06-07 | 2019-04-04 | 2019-04-12 | 2019-04-05 | 2019-04-06 | 0
| Design | 2 | 3 | 11 | 2019-06-07 | 2019-04-04 | 2019-04-12 | 2019-04-05 | 2019-04-06 | 1
| Cosmatic | 1 | 1 | 12 | 2019-06-07 | 2019-04-05 | 2019-04-12 | 2019-04-06 | 2019-04-06 | 0
| Edit | 1 | 0.5 | 12.5 | 2019-06-07 | 2019-04-05 | 2019-04-12 | 2019-04-06 | 2019-04-06 | -0.5
Subtotal: |  | 5 | 5.5
Project Plan | Plan | 1 | 1.5 | 14 | 2019-06-07 | 2019-04-10 | 2019-04-12 | 2019-04-10 | 2019-04-10 | 0.5
| Design | 3 | 3 | 17 | 2019-06-07 | 2019-04-10 | 2019-04-12 | 2019-04-10 | 2019-04-10 | 0
| Writing document | 2 | 2 | 19 | 2019-06-07 | 2019-04-10 | 2019-04-12 | 2019-04-11 | 2019-04-11 | 0
| Cosmatic | 1 | 0.5 | 19.5 | 2019-06-07 | 2019-04-10 | 2019-04-12 | 2019-04-11 | 2019-04-12 | -0.5
| Edit | 2 | 2 | 21.5 | 2019-06-07 | 2019-04-12 | 2019-04-12 | 2019-04-11 | 2019-04-12 | 0
Subtotal: |  | 9 | 9
Risk Analysis | Plan
Design
Writing document
Cosmatic
Edit
Subtotal: |  | 0 | 0
Storyboard | Plan
Research
Draft (Drawing)
Drawing
Subtotal: |  | 0 | 0
Prototype | Plan
Research
Create
Edit
Subtotal:
Completed Project | Plan
Research
Draft
Create
Testing
Edit
Subtotal: |  | 0 | 0
Total Hours: |  | 20 | 21.5
Differences (Budgeted - Actual Hours): |  | -1.5